## Sheet1
Expense Calculation
Workload p.p. | 180 hours
Project duration | 22 weeks
DEPARTMENT | COST (€ per hour) |  | WORK PACKAGE | COST |  | FIXED COSTS | PRICE (monthly) | DURATION (in month) | TOTAL COST
Project Manager | 34.3 |  | Project management (PM) | 15369.68 |  | Rent | 330 | 6 | 1980
Product manager | 28.5 |  | Development (DEV) | 21297.15 |  | Extra costs | 90 | 6 | 540
Leading Developer | 32.17 |  | Total | 36666.83 |  | Software and tools | 210 | 6 | 1260
System Architect | 30.56 |  |  |  |  | Provider services | 150 | 9 | 1350
Test Manager | 29.19 |  |  |  |  | Total |  |  | 5130
Documentation | 25.33
Product licence / Quarter | Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter 4
| Dep. |  | Dep. |  | Dep. |  | Dep.
Subscription (Deposit/ monthly) | 17 | 4.25 | 21 | 5.25 | 22 | 5.5 | 23 | 5.75
Lifetime licence | 2 | 5 | 3 | 7.5 | 4 | 10 | 4 | 10
Total | 17.75 |  | 22.75 |  | 26.5 |  | 27.25
Work hours / Employee |  | Leon Amtmann | Calvin Friedrich | Max Gohlke | Kevin Pauer | Thorsten Rausch | Tim Sellemann | Fabian Thomé
|  | (DOCU) | (Pm) | (LE) | (PL) | (SA) | (TM) | (LE)
| Project Management | 0 | 60 | 0 | 70 | 0 | 0 | 0
PM | Meetings | 30 | 30 | 30 | 30 | 30 | 30 | 30
| GitHub Organisation | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Presentation | 22 | 8 | 8 | 10 | 8 | 8 | 8
| Documentation | 90 | 15 | 10 | 20 | 10 | 15 | 10
| Analysis | 10 | 15 | 20 | 10 | 40 | 10 | 10
DEV | Design | 5 | 30 | 10 | 10 | 40 | 10 | 15
| Coding | 0 | 0 | 70 | 10 | 10 | 15 | 65
| Testing | 0 | 0 | 15 | 0 | 20 | 70 | 25
| Total (hours) | 162 | 163 | 168 | 165 | 163 | 163 | 168
PM |  | 57 | 163 | 43 | 115 | 43 | 43 | 43
DEV |  | 105 | 60 | 125 | 50 | 120 | 120 | 125